## Slide 1: Coordinating Multi-Site Trials
Christina Lomba, MS, CCRC
Clinical Trials Coordinator
Aflac Cancer & Blood Disorders Center

## Slide 2: Agenda
What is a Multi-Site Study?
Study Start-Up Procedures
  IND/IDE
  ClinicalTrials.gov
  Contracts
  IRB/regulatory
  Site Initiation Visit (SIV)
Active Study Procedures
  Enrollment
  Correlatives
  Reportable Events
  Monitoring/DSMB
  Communication
  Study Close-out

## Slide 3: Multi-Site Study
A multi-site study is one in which a local investigator designs a trial and oversees its conduct at multiple external institutions.
  This investigator is usually the study sponsor, as well.
Clinical Trial Coordinators (CTCs) aid these local investigators in opening and managing these multi-site trials for the duration of the study.
Aflac Cancer and Blood Disorders Center is currently coordinating 18 multi-site studies.
  Including investigational drug trials, registry studies, non-therapeutic intervention trials
  Ranging from 3 to 17 participating centers

## Slide 4: Study Start-Up
IND/IDE submission, if applicable
Local IRB approval
ClinicalTrials.gov registration, if applicable
Site selection
  Sites will be selected based on their capability to conduct the study protocol
Budget
  Typically includes start-up fees and per patient reimbursement

## Slide 5: IND vs IDE
IND = Investigational New Drug
  Applications are either Commercial or Research (non-commercial) under these categories:
    Investigator IND
    Emergency Use IND
    Treatment IND
IDE = Investigational Device Exemption
  Applications are either Significant or Nonsignificant risk under these categories:
    Commercial IDE
    Investigator-initiated IDE
    Emergency Use IDE
  Fda source

## Slide 6: IND Submission
What is submitted in an IND packet?
  IND Application Cover (Form 1571)
  Investigator’s Statement (Form 1572)
  Certification req’s, mandatory registration, & result reporting through ClinicalTrials.gov (if applicable)
  Animal Pharmacology and Toxicology Studies
  Manufacturing Information
  Clinical Protocols and Investigator Information

## Slide 7: IND Responsibilities
Control of drug- ensure investigational drugs are only shipped to investigators participating in the trials
Ensure labeling of immediate packing of investigational drug
Obtain and maintain critical documents (included in prior slide) and regulatory documents
Financial disclosures from each investigator
ClinicalTrials.gov registration
Annual reporting to the FDA
Evaluate and report on safety and effectiveness

## Slide 8: IDE Submission
Varies based on Risk level
What is submitted in an IDE packet?
  Sponsor information
  Report of prior investigations-all prior clinical, animal, and laboratory testing
  Investigational Plan (including protocol, etc.)
  Example agreements to be signed & certification all investigators have signed
  IRB and participating institution(s) information
  Labeling information
  Copies of Informed Consent forms and other material provided to subjects.

## Slide 9: IDE Responsibilities
Select and educate qualified investigators and monitors
Ensure/maintain FDA & IRB approval, reporting annually
Device Control-ensure investigational devices are only shipped to investigators participating in the trials
Obtain necessary signed agreements & financial disclosures from investigators
Ensure immediate package label of investigational device
Obtain and maintain critical documents (included in prior slide) and regulatory documents
ClinicalTrials.gov registration
Evaluate and report on safety and effectiveness

## Slide 10: ClinicalTrials.gov
ClinicalTrials.gov is a website resource that healthcare providers, patients, families, and the public have access to view clinical trials.
This includes basic information about the trial including:
  Brief summary
  Intervention
  Eligibility criteria
  Participating sites
  Study contact information
Once the study has been completed, results of the study will be posted.

## Slide 11: ClinicalTrials.gov Requirements
Required by law (FDAAA 801)
Required for Journal Publication
  Certain journals require registration
Required for studies meeting clinical trial definition

## Slide 12: ClinicalTrials.gov
Emory University Office of Clinical Research (OCR) is responsible for registering and maintaining this record.
  Study PI will need to confirm all information is entered accurately and is up-to-date.
If your study meets criteria to be registered, you will reach out to OCR@emory.edu to initiate the process.
One-time registration fee of $3,500 (includes updates, results reporting, etc.)
Study team/CTC is responsible for reaching out to OCR for any updates during the study including:
  Enrollment of first patient
  Study timelines
  Protocol amendments
  Additions of external sites
  Change of PI
  Contact information

## Slide 13
Process Flow | Responsible Party
Site Selection | Participating site is emailed study start-up packet.
 | Site reviews documents, initiates CTA negotiations, and returns pertinent information.
 | Site submits documents to the IRB and receives IRB approval. Site sends IRB approval to CHOA/Emory. CTA is fully executed.
Site Initiation Call | After the CTA has been fully executed, CHOA/Emory will schedule an SIV within 5-7 days.
Patient Eligibility | Site will contact CTC to check the status of enrollment and to request a reservation.
 | CHOA/Emory will review eligibility and will advise the site to complete patient registration and eligibility in REDCap (as applicable per study).
 | Site will upload the signed ICF & source documentation. Patient’s should be enrolled within the allotted time of making a reservation.
Patient Enrollment | CHOA/Emory will review and approve patient eligibility. The CTC will send an email confirming eligibility and assigning a subject ID number.
Study Entry | Obtain clinical & laboratory samples per protocol.
Treatment | Treatment as indicated per protocol
Final Visit/Follow-up | Complete follow-up & final visit studies and clinical samples per protocol.

## Slide 14: Start-up Package
A start-up package will be sent to sites and will contain all essential documents needed for the trial, including, but not limited to:
  Welcome Letter
  Protocol
  Consent and Assent (if applicable)
  Site Information sheet
  Clinical Trials Agreement
  Blank 1572 (if applicable)
  Financial Disclosure

## Slide 15: Contract
Once the Notice of Award (NOA) is received for your study, the CTC will request subcontracts from the relevant office at CHOA/Emory (Office of Sponsored Programs [OSP]/Office of Technology Transfer [OTT]).
Items needed for OSP to complete contract development:
  Protocol
  Site budget
  Statement of Work (SOW)
  Site contracts (the standard template will typically be used)

## Slide 16: Contract
Clinical Trials Agreement (CTA)-Legally binding agreement between the sponsor and participating institution. This will include:
    Obligations to Site and Investigator
    Terms and Terminations
    Indemnification
    Budget/Payment
    Confidentiality
    Publication
    Specimen/Tissue
    Intellectual Property
    Data Ownership
Contract negotiations will take place with the legal teams at both institutions.

## Slide 17: Contract
Other common agreements that may be used:
  Data Use Agreement (DUA)- agreement used for the transfer of data between research collaborators.
    CHOA- OSP; Emory- OSP
  Material Transfer Agreement (MTA) – agreement used for the transfer of material between research collaborators.
    I.e. blood, tissue, etc.
    CHOA-OSP; Emory- OTT
Negotiations may occur in parallel to IRB approval.
The agreement cannot be signed until the site has obtained local IRB approval.
A full executed copy will be retained in the trial master file.

## Slide 18: IRB
You must receive local IRB approval prior to sending any documents to the site.
The following will be sent to the sites for IRB approval
  Protocol
  Informed Consent Form (ICF)/Assent
  Local IRB approval letter
  Investigator Brochure (IB)
  Any manuals including Manual of Procedures of Operations, Pharmaceutical Manual, etc.
  Any other documents that received local IRB approval, including questionnaires, Case Report Forms (CRFs)

## Slide 19: ICF Documents
ICF documents will need to be amended at each site to include their institutions required language.
The coordinating site must review a participating site’s consent/assent documents prior to submitting the documents to their local IRB.
  This is to ensure the appropriate language is included and all requirements are met.

## Slide 20: Regulatory Documents
The following regulatory documents will be collected from sites at study start-up and maintained throughout the trial:
  1572 (if applicable)
  Financial Disclosure Forms
  Delegation of Authority Log (DOA)
  Training log(s)
  Investigational Product/Device log
  CVs, Licenses, and GCP training for all staff listed on DOA
  Laboratory reference ranges, CAP/CLIA, Lab Director’s CV and License (if applicable)
  Local IRB approvals

## Slide 21: Site Initiation Visit
A site initiation visit (SIV) is the process to ensure the principal investigator (PI) and site staff are sufficiently trained in executing the protocol.
Once the site has a fully executed contract and IRB approval, an SIV with the site will be scheduled within 5-7 business days.
This is typically conducted remotely for investigator-initiated trials.
Depending on the type of study, the following staff should be present for the training visit:
  PI
  Sub-investigators
  Study Coordinators
  Data Coordinator
  Regulatory Coordinator
  Pharmacists

## Slide 22: What is reviewed in an SIV?
Protocol overview
  Including background, aims, inclusion/exclusion criteria, treatment plan, study drug/device administration, SAE reporting, Off Protocol/Study criteria, stopping rules
Process flow
Study tools
  Training on the reservation of slots, electronic database, case report forms, patient enrollment, etc. as applicable
Study monitoring

## Slide 23: SIV Confirmation Letter

## Slide 24: SIV Follow-Up Letter

## Slide 25: What is involved after study start-up?
Study enrollment
Correlative Studies
Reportable Events
  Safety
  Deviations
DSMB
Data Queries and Monitoring
Site Payments
Study Communications

## Slide 26: Enrolling Patients
Most studies require Slot Reservation to ensure the study is not over enrolling.
  When a site identifies a patient, they must reach out to the CTC/PI to reserve a slot.
  The coordinating site will send a slot reservation survey to the site to complete.
    Typically, the patient must be enrolled within 14 calendar days of slot reservation.
    If the 14 calendar days are exceeded, they will need to re-reserve a slot.

## Slide 27: Enrolling Patients
Enrollment
  Once a patient has consented to the study, the study team will begin to complete the corresponding CRFs and have their local PI sign off and review.
    The site must include all relevant eligibility redacted source documentation.
  The study PI and CTC will review the patient for eligibility and deem them eligible or not.
  After the patient has been enrolled, they will need to follow the required timeline to start treatment.
    A patient typically needs to start treatment within 7 days of enrolling.

## Slide 28: Correlative Studies
Correlative studies
  May include whole blood, plasma, urine, tissue, stool etc.
Coordinating site will provide each site with:
  Lab kits
  Shippers
  Requisition form
Samples will be collected, processed (if applicable), and shipped to the receiving laboratory according to the study protocol and lab manual.
  Coordinating sites will communicate with the site and receiving laboratory about sample collections and projected arrival date.
If samples are not shipped same day of collection, the site will be required to maintain adequate freezer/refrigeration logs.

## Slide 29: Reportable Events- Safety
External sites will submit all AEs, SAEs, UPs, and SUSARs according to the study protocol.
  The SAE will be reported either in an electronic SAE form or in the study electronic database (REDCap).
  The local PI and study PI are required to review and assess the safety event.
External SAEs will be submitted to the local and coordinating site IRB and/or FDA, depending on the severity of the event and protocol requirements.
A copy of all significant safety events will be sent to the participating sites and the Data Safety Monitoring Board (DSMB).

## Slide 30: Reportable Events- Safety
SUSAR IND reporting
  For any suspected SUSAR, a MedWatch report will be submitted to the FDA within 15 calendar days.
  If the event is fatal or life-threatening, the report will be made within 7 calendar days.
If the trial also has a sponsor outside of CHOA/Emory that will be providing investigational drug, device, or funding, submission of SAEs may be a requirement.
  Separate reporting requirements for AEs, SAEs, UPs, and SUSARs

## Slide 31: Reportable Events- Deviations
External sites will submit all protocol deviations according to the study protocol.
  The deviation will be reported either in an electronic form or in the study electronic database (REDCap).
  The local PI and study PI are required to review and assess the event.
Deviations will be submitted to the local and coordinating site IRBs, if deemed necessary.
All deviations will be submitted to the DSMB.

## Slide 32: Data Safety Monitoring Board
Monitor Phase I and II trials and high-risk interventions, including multi-site trials.
Studies will receive a formal review by the Aflac DSMB once per quarter.
Patient safety information will be reviewed from all sites participating in the trial.
The DSMB will assess the safety of the study and send an official decision letter.
Sites PIs are responsible for sharing DSMB communication with their local IRBs.

## Slide 33: Querying Data
For the integrity of the trial, it is important to conduct frequent reviews of the data and submit queries to sites outside of the scheduled monitoring visits.
  Confirm data is being entered according to the schedule of events and within the designated timeframe listed in the protocol.
  Data is accurate and complete.
  Generate data queries and submit to designated staff member.

## Slide 34: Monitoring Visits
Monitoring visits are conducted by the CTC according to the schedule in the protocol in order to:
  Verify the investigator is conducting the study in accordance with Good Clinical Practice (GCP)
  To ensure the participants’ safety, rights, and well-being are being protected
  Data recorded in the CRFs is accurate, complete, and verifiable from source documentation

## Slide 35: Monitoring Visits
Type of monitoring visits
  Interim monitoring visits- routine visits scheduled according to the study protocol to ensure sites are following GCP and completing the data accurately and timely.
  For-cause visits- this will be at the discretion of the PI to address any unanticipated issues that arise, including safety concerns.
  Close-Out Visit (COV)- after the study has been completed, a COV will be conducted to retain all study documents and close out any unresolved data issues.

## Slide 36: Monitoring Visits
During the visit, the following documents will be reviewed:
  Regulatory documents
  CRFs for completeness and accuracy
  Source verification
  AEs and SAEs, ensuring all have been reported as necessary
  Protocol deviations
  Pharmacy records, if applicable
  Laboratory logs (refrigerator/freezer), if applicable

## Slide 37: Monitoring Visit Confirmation Letter

## Slide 38: Monitoring Visit Follow-up Letter

## Slide 39: Regulatory Files
      Maintain the following regulatory documents for the duration of the trial:
      All IRB approved versions of the protocol
      Approved ICF templates
      Local IRB approvals
      Study team licenses, CVs, GCP, and other relevant training documentation
      Local laboratory documentation
      Manual of Procedures (MOP), if applicable
      Standard Operating Procedures (SOPs)
      DSMB letters

## Slide 40: Site Payments
A W-9 must be completed from the participating institutions.
External sites will submit invoices according to the schedule agreed upon the CTA.
The study team will compare the invoice to the CTA payment-task/events to ensure all have been complete before processing the payment.
A copy of the invoice will be submitted to Emory or CHOA, depending on where the contract originated.
If the study is through Emory, Emory will be responsible for following up with the sites about invoices.

## Slide 41: Site Communication
Why is frequent communication important to have with sites?
  To ensure protocol integrity is being upheld
  Patient safety
  Provides the sites opportunities to ask questions
How is this typically done?
  Scheduled study meetings
  Newsletters
  Sending “check in” emails
    If there are active patients- email around every 2 weeks
    If there are not active patients- email around once per month

## Slide 42: Study Meetings
Depending on the rate of accrual and the type of trial, site calls are typically scheduled anywhere from monthly to quarterly.
Study meetings are held to:
  Keep sites engaged to keep up accrual
  Give sites opportunities to ask questions
  Provide a forum for providers to discuss patient concerns/questions
  Discuss protocol amendments
  Provide additional protocol training

## Slide 43: Study Newsletter
Another great form of communication to sites is newsletters.
Newsletters may include:
  Study contact information
  Frequently asked questions
  Study accrual numbers and goals
  General study updates
  Interim study results

## Slide 44: Study Close Out
Ensure sites have received all payments according to the CTA.
Conduct close-out visits
  Will be conducted remotely with all participating sites.
Close out the study with local and external IRBs.
  Sites will close out with their IRB after the close out visit has been conducted.
Post study results to ClinicalTrials.gov, if applicable.

## Slide 45: Close-Out Visit
Review of CRFs/eCRFs
Confirm appropriate source documentation is present for all subjects
Confirm all data management processes have been completed
  Confirm all CRFs have been completed and submitted
  Confirm all electronic queries issued to date have been appropriately resolved, reviewed, and closed.
Review AEs, UPs, SAEs, RNI
  They have been reported to all appropriate parties, if applicable

## Slide 46: Close-Out Visit
Review the Investigator Site Files
  Confirm all signed ICFs are on file for all subjects
  Ensure reporting of study closure to the IRB
  Reconcile study file with the master trial file including but not limited to:
    All IRB approved versions of the protocol
    Approved ICF templates
    Local IRB approvals
    All versions of the 1572
    Study team licenses, CVs, GCPs, and other relevant training
    Local laboratory documentation
    Standard Operation Procedures
    DSMB letters

## Slide 47: Close-Out Visit
Ensure the completeness of the following logs:
  Pre-screening log, Subject Screening and Enrollment log, Monitoring Visit log, Delegation of Authority Log, Training Attendance log(s), Investigational Product/Device Accountability Log, Specimen Tracking log, Freezer/Refrigeration log, Protocol Deviation log, and Adverse Event log
Investigational Product/Device Reconciliation (if applicable)
  Confirm IP dispense forms and accountability
  Confirm final disposition of IP per the MOP, sponsor requirements, etc.
Collected all laboratory specimens
  All specimens have been sent and analyzed
Confirm final disposition of study supplies or equipment

## Slide 48: Sources
1. https://www.fda.gov/drugs/types-applications/investigational-new-drug-ind-application
2. https://www.fda.gov/medical-devices/how-study-and-market-your-device/investigational-device-exemption-ide

## Slide 49: Q & A